## Dashboard
TIA Enterprise - delivery dashboard
Formulas over the other sheets. Edit blue cells on Task Tracker / Requirements / Acceptance Criteria.
Last updated | 2026-10-30
Tasks |  |  | Requirements (FR / PL / NFR) |  |  | Acceptance criteria
Total tasks | 100 |  | Total | 69 |  | Total | 41
Completed | 50 |  | Done | 14 |  | Done | 23
In progress | 0 |  | Partial | 19 |  | Partial | 2
Not started | 50 |  | Not started | 36 |  | Not started | 16
Blocked | 0 |  | % done | 20.29% |  | % done | 56.1%
% tasks completed | 50%
Consistency: Completed rows not at 100% | 0
By release
Release | Tasks | Completed | In progress | Not started | % tasks done | ACs done | ACs total
0 Specification | 6 | 6 | 0 | 0 | 100% | 0 | 0
R1 Platform foundation & cross-repo impact | 48 | 44 | 0 | 4 | 91.67% | 23 | 25
R2 Enterprise evidence & governance | 22 | 0 | 0 | 22 | 0% | 0 | 11
R3 Operational intelligence & scale | 10 | 0 | 0 | 10 | 0% | 0 | 2
R4 Extended coverage & advanced (GA) | 14 | 0 | 0 | 14 | 0% | 0 | 3
Total | 100 | 50 | 0 | 50 | 50% | 23 | 41
GA readiness (all requirements Done and all acceptance criteria Done) | NOT READY

## Task Tracker
ID | Release | Workstream | Task | Details / acceptance | Requirement refs | Output / location | Priority | Status | % Complete | Effort (rough) | Depends on | Next order | Completed on | Verified by | Notes
T-001 | 0 Specification | Specification | Review PRD v2.0 and companion documents | Critique; cross-document contradictions. | - | chat review | P0 | Completed | 100% | M |  |  | 2026-10-28 | Docs rendered and reviewed
T-002 | 0 Specification | Specification | Rewrite PRD v2.1, ARCHITECTURE v1.1, TFD v1.1 | Resolution strategies, severity model, canonical model, corrected diagrams. | - | revised/*.md, *.pdf | P0 | Completed | 100% | M |  |  | 2026-10-28 | Docs rendered and reviewed
T-003 | 0 Specification | Specification | Re-plan as enterprise product: PRD v3.0, ARCH/TFD v1.2 | Removed MVP/pilot; Releases 1-4; all requirements mandatory; FR-039..045, PL-001..012, AC-021..038. | - | revised/*.md, *.pdf | P0 | Completed | 100% | M |  |  | 2026-10-29 | Docs rendered and reviewed
T-004 | 0 Specification | Specification | SaaS multi-tenant model: PRD v3.1, ARCH/TFD v1.3 | Shared schema + RLS, dedicated option, PL-013..018, AC-039..041. | - | revised/*.md, *.pdf | P0 | Completed | 100% | M |  |  | 2026-10-29 | Docs rendered and reviewed
T-005 | 0 Specification | Specification | Resume file summary.md | Narrative log for session recovery. | - | summary.md | P0 | Completed | 100% | M |  |  | 2026-10-28 | Docs rendered and reviewed
T-006 | 0 Specification | Specification | Project tracker workbook | This file; requirement traceability. | - | TIA-Project-Tracker.xlsx | P0 | Completed | 100% | M |  |  | 2026-10-29 | Docs rendered and reviewed
T-007 | R1 Platform foundation & cross-repo impact | Engine | Canonical data model, statuses, path normalisation | Entities, evidence/analysis statuses. | FR-008 FR-010 | tia/models.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_normalize_path
T-008 | R1 Platform foundation & cross-repo impact | Engine | Read-only git access | Revisions, trees, diffs; never executes repo code. | FR-002 | tia/gitutil.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | acceptance tests | Local clones only until GitHub App connector
T-009 | R1 Platform foundation & cross-repo impact | Extraction | Python adapter: endpoints, schemas, functions, outbound calls, tests | FastAPI/Flask, pydantic, requests/httpx, generated clients. | FR-004 FR-012 FR-017 | tia/extract_python.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_units.py, AC-002/004
T-010 | R1 Platform foundation & cross-repo impact | Resolution | Cross-repo resolution R1, R2, R3, R5 + corroboration | Service map (R4) input; never by name alone. | FR-014 | tia/resolve.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | AC-004/018/019 tests
T-011 | R1 Platform foundation & cross-repo impact | Engine | Typed graph, test association | Impact-direction index; import/HTTP/naming association. | FR-013 FR-021 | tia/graph.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | AC-003/006 tests
T-012 | R1 Platform foundation & cross-repo impact | Engine | Basic REST contract diff | P0 list; others 'not evaluated'. | FR-018 | tia/contracts.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_removed_endpoint_is_breaking
T-013 | R1 Platform foundation & cross-repo impact | Engine | Severity and materiality rules | Change nature x criticality; inferred cap. | PRD-7.3 | tia/severity.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_severity_*
T-014 | R1 Platform foundation & cross-repo impact | Engine | Impact engine: bounded traversal, unknowns, status | Two-pass BFS, limits, coverage, status semantics. | FR-013 FR-015 FR-016 | tia/impact.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | AC-009/010/012 tests
T-015 | R1 Platform foundation & cross-repo impact | Reporting | JSON report, PR comment renderer, audience redaction | Single-marker advisory comment; no leaks. | FR-035 PL-002 | tia/report.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | AC-016/020 tests
T-016 | R1 Platform foundation & cross-repo impact | Interfaces | CLI analyze + FastAPI wrapper | Synchronous API; header-based audience placeholder. | PL-008 | tia/cli.py, tia/api.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_api.py
T-017 | R1 Platform foundation & cross-repo impact | Connectors | Repository ingestion service: GitHub, Azure DevOps, any git URL, file:// URL, local path | Clone/sync via git; PAT via env only; PR ref fetch by number; merge-base; friendly errors; host allow-list; local paths gated. | FR-001 FR-039(partial) | tia/repos.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_ingest.py (real git repos; real GitHub clone checked manually) | Token auth for private repos untested against real ADO/GitHub (no credentials here)
T-018 | R1 Platform foundation & cross-repo impact | Connectors | Bulk discovery: whole ADO project / GitHub org or user | REST listing + ingest all; supports on-prem ADO / GHE api_base. | FR-001 | tia/repos.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_discover_ado_and_github (fake API servers only) | Needs real PAT to verify
T-019 | R1 Platform foundation & cross-repo impact | Interfaces | Web UI v0 + server entry point | Ingest (URL / discovery / path), repo list with sync/remove, analysis (branch or PR), report, unknowns, PR-comment markdown. | PRD-9 (partial) | tia/web/index.html, tia/server.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | manual run + test_api_end_to_end_with_demo_landscape | Dev mode: no auth, no tenancy; not the R2 UI
T-020 | R1 Platform foundation & cross-repo impact | Graph | Code / dependency graph explorer v0 | Services, endpoints+schemas, and function-level views from the persisted extracts; filter by repo, search, focus (neighbourhood), node limit with truncation notice; evidence-coloured edges; unresolved calls shown; node/edge detail panel with file:line evidence. | PRD-9.2 | tia/graphview.py, tia/api.py (/api/v1/graph*), tia/web/index.html, tia/web/vendor/cytoscape (bundled, MIT) | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_graph.py (8) + headless Chrome run: all 3 levels, search, focus, details, 0 console errors | Graph is rebuilt from cached extracts per request (not a persisted graph store yet)
T-021 | R1 Platform foundation & cross-repo impact | Graph | Impact overlay on the graph | Changed component -> via -> affected, edges by evidence status, nodes coloured by severity, one click from the report. | PRD-9.2 FR-013 | tia/graphview.py (impact_overlay), /api/v1/impact-analyses/{id}/graph | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_graph_api_and_impact_overlay + headless Chrome run
T-022 | R1 Platform foundation & cross-repo impact | Platform | Multi-tenant PostgreSQL storage: schema, SQL migrations, forced RLS, tenant-bound transactions | tenants registry; tenant_id on every row; FORCE ROW LEVEL SECURITY; runtime role tia_app (not owner, no BYPASSRLS, no access to registry); set_config per transaction; connection pool; migration runner; SQLite removed. | PL-003 AC-035 TFD-9 | tia/db.py, tia/store.py, tia/migrations/0001_init.sql, tia/migrate.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_storage.py (isolation, no-tenant, unfiltered delete, privileges, forced RLS) on real PostgreSQL 16.2; whole suite (69) now runs on PostgreSQL | Embedded PostgreSQL 16.2 only; a managed PG / PgBouncer deployment is untested (set_config is transaction-local so transaction pooling is safe by design). Tenant is fixed per process until SSO (UC1-18/19).
T-023 | R1 Platform foundation & cross-repo impact | Security | Tamper-evident, append-only, keyed (HMAC) audit chain per tenant | Advisory-locked sequential chain; runtime role has INSERT/SELECT only; HMAC key kept outside the DB so an owner cannot recompute the chain; verify endpoint; repository register/sync/PR-fetch/remove audited (no tokens). | 11.3 | tia/store.py (audit, verify_audit), /api/v1/audit, /api/v1/audit/verify | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests: tamper, delete, reorder, append-only, 48 concurrent writes, keyed-vs-unkeyed owner rewrite, no secrets in audit | Audit of GitHub/ADO comment posting and logins is added with those items
T-024 | R1 Platform foundation & cross-repo impact | Platform | Job queue + worker: idempotent, newest-wins, fair across tenants, exact per-tenant cap, retries with backoff, leases | jobs table under RLS; tia_worker role is the only one that sees all tenants' jobs; enqueue/claim/heartbeat/succeed/fail/reap; worker loop with PermanentError; shared resolve/execute service used by sync API and worker; ?async=true API, job status and cancel endpoints; tokens refused in queued work. | PL-017 AC-040 TFD-8 TFD-12 | tia/jobs.py, tia/worker.py, tia/analysis_service.py, tia/migrations/0002_jobs.sql, /api/v1/jobs | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_jobs.py (20): idempotency, supersede, cancel, force, role isolation, fairness, cap (also under 12 concurrent claims), retry/backoff/permanent, lease recovery + stale worker, 6 workers x 30 jobs exactly once, API->queue->worker end to end; repeated 4x stable; live run on the dev server | Real PostgreSQL 16.2. Workers share the repo filesystem path with the API (shared volume / object store is a deployment item under UC1-23). Fairness is round-robin by queued position, not weighted by plan.
T-025 | R1 Platform foundation & cross-repo impact | Platform | Persisted versioned graph + per-file incremental extraction + full-rescan path | Per-file facts cached by git blob id; content-addressed immutable graph versions with a head per landscape; head advances on register/sync/delete/webhook; POST /graph/rescan re-derives everything, detects drift against the incremental result and repairs it. | FR-003 AC-021 | tia/extraction.py, tia/graphstore.py, tia/migrations/0003-0004, /api/v1/graph/versions, /api/v1/graph/rescan | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_incremental.py (7), tests/test_graph_versions.py (9): incremental result and graph equal a full rescan; a one-file push adds exactly one cached file fact end to end; tenant isolation; rescan detects and repairs a corrupted cache | Python adapter only (Java is UC1-07). Real PostgreSQL 16.2 + real git.
T-026 | R1 Platform foundation & cross-repo impact | Platform | Stale-relationship handling + repository freshness (scan state) | Cross-repo relationship history (current ¦ stale: scan_failed, parse_failed, evidence_removed); repos track scan status, last successful scan and analysed revision; reports carry per-repo freshness, a repository_freshness unknown, status partial on a failed scan, and stale-evidence findings capped at Medium; graph view draws stale edges as stale. | FR-005 FR-010 AC-011 AC-022 | tia/relationships.py, tia/repos.py (scan state), tia/impact.py, tia/migrations/0005, /api/v1/graph/relationships | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_stale.py (6): failed scan -> stale finding + last good scan stated -> recovery; removed call; unparseable consumer file; repository removal; redaction; no needless rewrites | runtime_observed evidence (R6) still never produced. No interim 'pending re-scan' state between a push and the synchronous refresh.
T-027 | R1 Platform foundation & cross-repo impact | Platform | Evidence snapshot materialisation + reproduction | Immutable snapshot per analysis (revisions of every repo incl. target head, extractor/config versions, graph version, freshness and stale-relationship state); commits pinned in TIA clones; POST /impact-analyses/{id}/reproduce re-runs on the snapshot and reports identical or not; evidence view shows the path and revision of each hop of every material finding. | AC-015 | tia/migrations/0006, tia/analysis_service.py (reproduce, pin_analysis), tia/report.py (evidence_view), /api/v1/evidence-snapshots, /impact-analyses/{id}/evidence¦reproduce | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_snapshots.py (8): identical after the landscape moved on; stale state pinned; pins survive history rewrite and gc (and without pins TIA says the evidence is gone); immutable by privilege; tenant isolation; audience redaction | Local repositories are read in place and cannot be pinned (a rewritten local history makes reproduction fail with a clear message).
T-028 | R1 Platform foundation & cross-repo impact | Connectors | Code upload from the user's drive: zip and whole folder, 2 GiB cap | Session-based upload API (zip streamed as one body, folder in batches), safe extraction (traversal/absolute/drive/device names, ADS, symlinks, encrypted, case collisions rejected; caps enforced on bytes written), each upload a git commit so two uploads are analysed like a PR; UI tab with progress; one-call PUT for scripts. | FR-001 | tia/upload.py, tia/api.py (/api/v1/uploads, /repositories/{name}/upload, /revisions), tia/web/index.html | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_upload.py (33); real Chrome (zip + folder + analyse vs previous upload, 0 console errors); live 721 MB zip streamed with 2 MB server memory growth; declared 3 GB refused with 413 | Per-upload cap only: no per-tenant total storage quota yet (UC1-20/21). Uploaded code is parsed, never executed. Uploads are snapshots (files absent from a re-upload are removed).
T-029 | R1 Platform foundation & cross-repo impact | Extraction | Java / Spring adapter (REST): routes, DTO schemas, RestTemplate/WebClient/RestClient/OpenFeign/shared clients, JUnit + MockMvc tests | tree-sitter-java parser; Spring Web endpoints (class prefix, arrays, RequestMethod lists, controller interfaces), request/response schemas incl. wrappers, records, entities, inheritance and Jackson naming; base URLs from constants, @Value, environment, WebClient/RestTemplate builders; Feign and shared-client calls resolved at assembly (R2/R1); spring.application.name as default service identity; unsupported HTTP client libraries disclosed as an unknown; per-file incremental caching preserved. | FR-004 FR-012 FR-017 AC-023 | tia/extract_java.py, tia/extract_python.py (assembly), tia/extraction.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_java.py (35): facts, cross-language Python<->Java and Java<->Java resolution, impact on real branches, parse failures, incremental == full rescan; run on real third-party code (spring-petclinic-microservices: 54 files, 0 parse failures, 16 endpoints, the 2 real service-to-service calls resolved source_confirmed) | Spring MVC/WebFlux/OpenFeign only (no JAX-RS, Micronaut, Quarkus, Spring Cloud Gateway routes); OkHttp/Apache/java.net.http/Retrofit calls are reported as unknown, not analysed; @RequestMapping without a method is read as GET; dynamic base URLs stay unresolved; variable types are resolved per file by name; endpoint auth config (FR-017) not extracted; no accuracy measurement yet (UC1-25).
T-030 | R1 Platform foundation & cross-repo impact | Extraction | Python ORM + migration extraction: SQLAlchemy (declarative, Mapped, Flask-SQLAlchemy), SQLModel, Django models; Alembic and Django migrations | Entities -> tables -> columns (nullability, keys, FK and many-to-many link tables, inherited mixins and Django auth bases); model references inside functions classified read/write (objects.*, session.query/add/delete, select/insert/update/delete, save(), self/cls); Alembic upgrade() ops incl. batch_alter_table and op.execute SQL; Django CreateModel/AddField/RemoveField/AlterField/RenameField/DeleteModel/RenameModel/AlterModelTable/RunSQL; raw SQL, Table() objects, dynamic table names, RunPython and unknown bases reported as data access not analysed. | FR-006 FR-006a | tia/extract_orm.py, tia/extract_data.py, tia/extract_python.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_data.py (58 incl. Python models, references, Alembic, Django); run on real third-party code: django-realworld-example-app (5 models, 5 link tables) and fastapi full-stack template (SQLModel + 5-revision Alembic chain) - replayed migration schema equals the ORM columns exactly | Django app label is taken from the directory (a custom AppConfig label would change table names); model references are resolved by simple name per repository and local variable types by assignment/annotation only; a model name used in two apps is reported ambiguous; Python is parsed with the server interpreter, so newer syntax (e.g. Python 3.14 'except A, B:') is a parse failure, reported as partial.
T-031 | R1 Platform foundation & cross-repo impact | Extraction | Java ORM + migration extraction: JPA entities, Spring Data repositories, Flyway SQL, Liquibase XML/YAML/JSON | Entities (@Table/@Column/@JoinColumn/@JoinTable, Spring Boot naming strategy, @MappedSuperclass/@Embedded merge, @Transient), repository methods classified read/write by name and @Query/@Modifying/native queries (entities named by the query included), SQL DDL parser for PostgreSQL/MySQL/Oracle/SQL Server/HSQLDB statements, Liquibase createTable/addColumn/dropColumn/renameColumn/modifyDataType/not-null/dropTable/renameTable/sql; spring.datasource.url and tia-services.yaml database identity; EntityManager/JDBC/jOOQ/MyBatis, procedural SQL, stored procedure calls, custom naming strategy, @Inheritance and undeclared join tables reported as not analysed. | FR-006a AC-023 | tia/extract_java.py, tia/extract_data.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_data.py; run on real third-party code: spring-petclinic (6 entities, 20 repository accesses, 3 schema scripts, 0 unparsed), jhipster-sample-app (593 files: 5 entities, 7 Liquibase changelogs, 75 accesses, EntityManager/JDBC reported) - replayed Liquibase schema equals the JPA columns exactly; real-code runs found and fixed HSQLDB 'DROP TABLE x IF EXISTS', the org.springframework package-name filter and Django to= keyword / self-referential M2M | Spring Data repositories are resolved only when they extend a Spring Data interface directly; default join-table names are not derived (reported); Liquibase files are found by 'changelog'/'liquibase' in the path; Flyway undo scripts ignored; XML with a DOCTYPE is refused (entity-expansion safety); several database flavours of one schema script in one repository are replayed together; Kotlin entities not supported.
T-032 | R1 Platform foundation & cross-repo impact | Engine | Data-impact traversal and findings (AC-024): schema change -> mapped entities -> reading/writing functions -> endpoints -> API consumers | Data layer in the graph (entity, table, column, migration; MAPS_TO, MAPS_COLUMN, READS, WRITES, MIGRATES); tables belong to a database and services are linked only through a shared declared/URL-named database, never by table name; migration ops the head adds classified against the replayed schema (drop/rename table or column, type change vs provable widening, NOT NULL tightening, required new column = breaks writers only); findings per entity with accessors, own-repository rules (SEV-DATA-MAPPING-BROKEN / SEV-DATA-UPDATED), propagation through the existing call/endpoint/consumer traversal, unknowns for database identity, unanalysed data access, unparsed migration statements and unmapped changes; comment, redaction, graph view and impact overlay support the new node types. | FR-015 AC-024 | tia/data.py, tia/impact.py, tia/severity.py, tia/report.py, tia/graphview.py, tia/web/index.html | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_data.py (58); live: dev server on real PostgreSQL, real HTTP, queue + worker for 8 branches across Flyway/Liquibase/Alembic/Django, reproduce identical, real Chrome (findings table, impact overlay column -> 3 entities -> functions -> endpoints -> portal call sites, column search, 0 console errors) | Column-level precision only for columns an analysed entity maps; type/nullability compatibility is not evaluated beyond provable widening; services using a database without a declared identity are assumed private (stated as an unknown); views, stored procedures and raw SQL are FR-041 (not built); same-repository functions reading a changed table are reported as direct low findings.
T-033 | R1 Platform foundation & cross-repo impact | Platform | Tenant lifecycle: provision, SCM installation mapping, suspend/resume, offboard with deletion certificate; per-tenant storage quota | tenants admin class + CLI; suspended tenants get 403 tenant_suspended and their queued jobs are not claimed; offboarded 410; quota 403 storage_quota_exceeded; offboarding deletes every tenant table and returns a hashed certificate that verify_deletion re-checks. | PL-013 AC-039 | tia/tenants.py, tia/gate.py, tia/migrations/0007_tenant_lifecycle.sql | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_tenants.py (21); live: admin CLI + API + worker processes on PostgreSQL | No billing/metering; SCM installation mapping is stored but a real GitHub App installation event is not wired (UC1-04).
T-034 | R1 Platform foundation & cross-repo impact | Interfaces | GitHub check run (always neutral) + POST publish endpoint for the PR comment; permalink in the comment | check_run_payload (annotations <=50), upsert_check_run, publish_to_github, audit_publication; ScmConfig.check_run/public_url. | FR-035 AC-020 | tia/github.py, tia/publish.py, tia/api.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_publish.py (22) and tests/test_webhooks.py against a fake GitHub; comment upsert verified live on github.com earlier | Check runs need a GitHub App token: simulated only, NOT verified against real GitHub.
T-035 | R1 Platform foundation & cross-repo impact | Interfaces | Permalink report page per analysis | Server-rendered no-JS page GET /analyses/{id}: escaped, stacked cards under 700px, CSP + nosniff. | PRD-9 | tia/reportpage.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_reportpage.py (11) + real Chrome desktop and mobile widths
T-036 | R1 Platform foundation & cross-repo impact | Security | Secrets management and encryption: envelope encryption of tenant secrets, secret references, scrubbing, TLS enforcement | KEK in a secrets manager (file/Vault Transit) -> per-tenant versioned DEK -> AES-256-GCM with tenant+name+version as AAD; refs file:/vault:/env:/NAME_FILE; scrub of token formats from graph, reports, logs, audit and job errors; refuses tokens over plaintext http, HSTS. | PL-011 | tia/credentials.py, tia/secretstore.py, tia/scrub.py, tia/transport.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_credentials.py (32), tests/test_secretstore.py (49); Vault only against a FAKE (KV v2 + Transit) | NOT verified: real Vault, AWS KMS/Azure Key Vault wrappers (not built), customer-managed keys, PostgreSQL TLS handshake (embedded PG has no TLS).
T-037 | R1 Platform foundation & cross-repo impact | Platform | Platform observability: Prometheus metrics, JSON logs, W3C traces to OTLP, health/readiness | Dependency-free metrics registry, request-id logs, traceparent through the queue into the worker, OTLP/HTTP JSON exporter, /healthz /readyz /metrics (token-protected), worker heartbeats and worker metrics port. | PL-007 | tia/metrics.py, tia/obs.py, tia/tracing.py, tia/health.py, tia/telemetry.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_observability.py (57); live API+worker processes; OTLP only against a fake collector | NOT verified against a real Prometheus/OTel collector; no dashboards/alert rules shipped.
T-038 | R1 Platform foundation & cross-repo impact | Engine | Configuration management: versioned per-tenant limits, severity overrides, criticality, gateway prefixes, comment audience | Strict validation (all problems at once), immutable insert-only versions, diff/restore, limits are defaults and ceilings, overrides recorded not silent, reproduce uses the snapshot's config; API + admin CLI + UI panel. | PRD-7.3 | tia/tenantconfig.py, tia/severity.py, tia/migrations/0010_tenant_config.sql | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_tenantconfig.py (65); live CLI -> API -> worker processes; real Chrome panel | Only critical criticality changes severity; no approval workflow/RBAC (needs SSO UC1-18/19).
T-039 | R1 Platform foundation & cross-repo impact | Security | SSO: OIDC (authorization code + PKCE, bearer tokens) and SAML 2.0 (SP-initiated); service-account tokens; browser sessions | Per-tenant identity providers; JWT verification limited to asymmetric algorithms with the key chosen by kid; provider fetches only to public https addresses; single-use sign-in state bound to the browser; SAML needs a signed assertion by a configured certificate (rotation supported), refuses XXE, signature wrapping, replay, unsolicited responses; service tokens carry roles and a repository scope, expire and are revocable, only their hash is stored; the credential names the tenant, so one deployment serves many tenants. | PL-001 AC-025 | tia/jwtverify.py, tia/netsafe.py, tia/identity.py, tia/oidc.py, tia/saml.py, tia/authapi.py, tia/migrations/0011_identity.sql | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_auth.py, tests/test_auth_api.py, tests/test_saml.py; live: admin CLI + API process + real Chrome through a real OIDC flow (4 people, sign-out, role change, CSRF, token shown once) | Tested only against our own OIDC and SAML provider implementations: no real Entra/Okta/Keycloak/ADFS, so interoperability quirks (group-overage claim, signed AuthnRequests, encrypted assertions, single logout) are unverified; SHA-1 refusal in SAML not exercised; rate limiting left to a reverse proxy.
T-040 | R1 Platform foundation & cross-repo impact | Security | RBAC (5 roles) and per-repository access mirrored from GitHub; PR comment names another repository only if all readers may read it | Deny-by-default route table (a test fails on an unclassified route); roles additive, from identity-provider groups or administrator assignment; repository modes scm/restricted/tenant; mirror of GitHub collaborators (fail closed when missing, stale or failed); unreadable repositories are 404 everywhere and reports are redacted per reader with a count of what was omitted; administrators are not exempt; actor recorded on every audited action. | PL-002 AC-016 AC-025 | tia/rbac.py, tia/access.py, tia/authapi.py, tia/api.py, tia/migrations/0012_repo_access.sql | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_access.py (34) against a fake GitHub REST API; live in real Chrome: four people see different repositories and differently redacted reports for the same analysis | Mirror tested against a FAKE GitHub API only; Azure DevOps permission mirroring not built (UC1-06/15); the webhook receiver still uses the deployment's default tenant.
T-041 | R1 Platform foundation & cross-repo impact | Connectors | GitHub App connector: App JWT, installation tokens, tenant routing by installation, repository discovery, permission-failure reporting | RS256 App JWT (9 min) -> installation token (cached, refreshed 5 min early) used for clone/fetch, comments and REAL check runs; a webhook is routed to the tenant that owns its installation (SECURITY DEFINER lookup of active tenants only); an installation is linked by the operator (CLI) or by a tenant administrator who proves through GitHub user authorisation that they can see it; repositories of the organisation's installations can be discovered and ingested; a removed/suspended installation or a repository the App cannot see is reported as such and fails the job permanently; tokens and the key never reach logs, audit or the database. | FR-001 AC-026 | tia/githubapp.py, tia/api.py, tia/analysis_service.py, tia/migrations/0013_github_app.sql | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_githubapp.py (51) against a GitHub platform stand-in that verifies the App JWT with the real public key and accepts check runs only from installation tokens; live: admin CLI + API process + worker process (signed webhook -> job in the owning tenant -> comment + check run, nothing in the other tenant, no token or key in logs) | NOT verified against real GitHub: no real App registered, so GitHub's actual permission model (e.g. what listing collaborators needs), rate limits and the user-authorisation redirect are untested; installation_repositories events are acknowledged only; Azure DevOps equivalent is UC1-06/15.
T-042 | R1 Platform foundation & cross-repo impact | Quality | CI pipeline for TIA: tests on Python 3.10-3.12, package check, migration and tenant-table gates, secret scan, dependency audit | GitHub Actions workflow (least-privilege, no secrets, no pull_request_target, timeouts) plus tools/ci.py that runs the same gates locally; each gate is itself tested to fail on what it exists to catch. | - | .github/workflows/tia-ci.yml, tools/ci.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_ci.py (15); tools/ci.py workflow/migrations/secrets/package run locally and pass; the real workflow file parsed and checked | The workflow has NOT run on GitHub Actions (nothing is pushed: origin is not the user's repository); actions are pinned by tag, not by commit SHA; pip-audit runs only in CI; no lint/type-check stage yet.
T-043 | R1 Platform foundation & cross-repo impact | Quality | Accuracy harness and reference landscapes (PRD 15.3): two independent Java references on real third-party code plus a synthetic Python landscape | tools/accuracy.py measures recall, precision, findings per PR, resolution rate, traceable evidence, silent pass and source_confirmed-without-evidence against curated truth (dependencies with proof lines, endpoints, must-not-link calls, patched changes), segmented by language, relationship, difficulty, strategy and evidence; first contact found and fixed three real gaps (local-variable URLs, service-discovery hosts, files that stop parsing reported as removed declarations). | PRD-15 15.3 | tools/accuracy.py, reference/, tia/extract_java.py, tia/impact.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_accuracy.py (14); spring-petclinic-microservices recall 6/6, precision 8/8, resolution 6/6; piggymetrics recall 3/3, precision 6/6, resolution 3/4; synthetic 4/4 and 15/15; every measured PRD 15.3 target met on all three | Small samples; only two independent references and both are Java (no independent Python multi-service reference found); piggymetrics is found only with paths.strip_prefixes configured by hand (0/3 without it: TIA does not read context paths from config); the -30% assessment-time target needs a user study (NOT MEASURED); customer landscapes must be measured at onboarding.
T-044 | R1 Platform foundation & cross-repo impact | Quality | Performance benchmark at 500 repositories (PRD 12): scan, incremental PR analysis, interactive report, 50-job burst, determinism | tools/benchmark.py generates a Python+Java landscape of real git repositories and measures through production code and a real PostgreSQL. The first full run found 44 s per PR analysis (one git process per repository, repeated); fixed by reading refs from files, caching, parallel resolution and one query per analysis. | PRD-12 | tools/benchmark.py, tia/gitutil.py, tia/impact.py, tia/analysis_service.py, docs/PERFORMANCE.md | P0 | Completed | 100% | M |  |  | 2026-10-28 | 500 repositories / 605 101 lines: PR analysis P95 5.3 s (target 120 s); report P95 0.07 s (5 s); burst of 50 jobs on 8 workers all completed, P95 163 s (180 s); scan 260 s; re-analysis identical | Generated landscape, not 20 M lines of real code (the 4 h scan target is not demonstrated at that size); burst margin is thin (163 s of 180 s) on one machine with the database local; availability/RPO/RTO not measured.
T-045 | R1 Platform foundation & cross-repo impact | Quality | Security review and threat model (PRD 19 gate) | docs/SECURITY.md: assets, trust boundaries, 19 threats with mitigations and tests; an independent read-only code review found 2 high and 8 medium issues; all high and all but one medium fixed with regression tests (tests/test_security_review.py). | PRD-19 | docs/SECURITY.md, tests/test_security_review.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | Independent AI code review of the auth, tenant-routing, access, GitHub App and SQL code; 29 regression tests; no critical/high open | NOT an external penetration test; M7 (first-come claim of a public issuer/audience pair) is open and only mitigated; upload extraction, worker handlers, git argument handling, offboarding crypto and report-page XSS were not independently reviewed.
T-046 | R1 Platform foundation & cross-repo impact | Docs | Administrator guide, user guide and API reference that cannot drift from the code | docs/ADMIN-GUIDE.md, docs/USER-GUIDE.md and docs/API.md (generated from the route table and OpenAPI schema); tests check every environment variable, command, endpoint, link and configuration example against the code and the real validators. | - | docs/, tools/gen_docs.py, tests/test_docs.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | tests/test_docs.py (11) | Written from the code and tests, not from field experience; no screenshots; API descriptions are only as good as the handler docstrings.
T-047 | R1 Platform foundation & cross-repo impact | Interfaces | GitHub comment upsert (code) | Not yet verified against live GitHub. | FR-035 | tia/github.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | marker helper test only
T-048 | R1 Platform foundation & cross-repo impact | Platform | SQLite evidence cache, analysis store, JSONL audit | Interim store; replaced by PostgreSQL in R1. | 11.3 | tia/store.py | P0 | Completed | 100% | M |  |  | 2026-10-28 | test_audit_and_cache
T-049 | R1 Platform foundation & cross-repo impact | Quality | Demo landscape fixture + 29 tests | 6 git repos; AC-mapped tests. | PRD-14 | fixtures/, tests/ | P0 | Completed | 100% | M |  |  | 2026-10-28 | 29 passed
T-050 | R1 Platform foundation & cross-repo impact | Quality | Separate production code from support code | tia/ = production only; tools/demo.py. | - | tia/, tools/ | P0 | Completed | 100% | M |  |  | 2026-10-28 | 29 passed
T-051 | R1 Platform foundation & cross-repo impact | Connectors | PR comment + live verification via GitHub App | Update in place on push; never blocks merge. | FR-035 AC-020 |  | P0 | Not Started | 0% | S | GitHub App | 1
T-052 | R1 Platform foundation & cross-repo impact | Delivery | Container images, Docker Compose, Helm chart | Images for SaaS and dedicated; documented data locations. | PL-009 |  | P0 | Not Started | 0% | M | PostgreSQL, queue | 2
T-053 | R1 Platform foundation & cross-repo impact | Delivery | SaaS production environment (first region) | Infrastructure as code, gateway with tenant resolution and rate limits, managed PostgreSQL, evidence store, secrets, monitoring. | PL-009 PL-007 |  | P0 | Not Started | 0% | L | Containers | 3
T-054 | R1 Platform foundation & cross-repo impact | Release | R1 release quality gate | All R1 ACs, accuracy, performance, security, operability, docs. | PRD-19 |  | P0 | Not Started | 0% | S | All R1 tasks | 4
T-055 | R2 Enterprise evidence & governance | Verification | CI test-result ingestion | Test identity, result, run, commit/build. | FR-022 AC-027 |  | P1 | Not Started | 0% | M
T-056 | R2 Enterprise evidence & governance | Verification | Coverage enrichment | Exists / associated / passed / executed / validated. | FR-023 AC-027 |  | P1 | Not Started | 0% | M | CI results
T-057 | R2 Enterprise evidence & governance | Verification | Regression recommendations + missing-test evidence | Explain relevance; never 'safe to skip'. | FR-024 FR-025 |  | P1 | Not Started | 0% | M | CI results
T-058 | R2 Enterprise evidence & governance | Contracts | Full API contract comparison + OpenAPI ingestion | Enum narrowing, shapes, auth config, configurable compatibility rules. | FR-018 |  | P1 | Not Started | 0% | M
T-059 | R2 Enterprise evidence & governance | Contracts | Event and message contracts (JSON Schema, Avro, Kafka) | Producers/consumers, schema diff. | FR-007 FR-019 FR-020 AC-028 |  | P1 | Not Started | 0% | L
T-060 | R2 Enterprise evidence & governance | Runtime | Telemetry ingestion and R6 runtime edges | OpenTelemetry extracts; window + environment. | FR-026 FR-027 FR-014 AC-007 AC-008 |  | P1 | Not Started | 0% | L
T-061 | R2 Enterprise evidence & governance | Runtime | Deployment correlation and environment views | Proposed vs deployed revision per environment. | FR-028 FR-029 AC-029 |  | P1 | Not Started | 0% | L
T-062 | R2 Enterprise evidence & governance | Governance | Ownership and criticality registry connector | Backstage/catalog or admin-managed. | FR-033 |  | P1 | Not Started | 0% | M
T-063 | R2 Enterprise evidence & governance | Governance | Release-policy engine | pass/fail/not_evaluated/requires_review; versioned policies. | FR-033 FR-034 AC-013 AC-014 |  | P1 | Not Started | 0% | L
T-064 | R2 Enterprise evidence & governance | Governance | Advisory and enforcement modes | Report to repository protection; customer-configured. | FR-036 AC-030 |  | P1 | Not Started | 0% | M | Policy engine
T-065 | R2 Enterprise evidence & governance | Integration | GitHub check run | Policy outcomes in a check run. | FR-035 |  | P1 | Not Started | 0% | M | Policy engine
T-066 | R2 Enterprise evidence & governance | Integration | ITSM change-record integration (ServiceNow) | Write-only attachment keyed by change id. | FR-038 AC-031 |  | P1 | Not Started | 0% | L
T-067 | R2 Enterprise evidence & governance | Integration | MCP server and read API for assistants | Read-only report retrieval. | FR-037 AC-032 |  | P1 | Not Started | 0% | M
T-068 | R2 Enterprise evidence & governance | UI | Web UI: report, path explorer, filters, unknowns panel | React; API-first. Extend the v0 graph: filters by severity/evidence/environment, saved views, path highlighting, accessible table alternative, scale to large landscapes (server-side clustering). | PRD-9 PRD-9.2 |  | P1 | Not Started | 0% | XL
T-069 | R2 Enterprise evidence & governance | UI | Administration console | Connectors, service map, policies, rules, retention. | PL-006 |  | P1 | Not Started | 0% | L | Web UI
T-070 | R2 Enterprise evidence & governance | UI | Accessibility WCAG 2.1 AA | Audit + fixes. | PL-012 |  | P1 | Not Started | 0% | M | Web UI
T-071 | R2 Enterprise evidence & governance | SaaS | Usage metering and plan limits | Per-tenant repositories/analyses/users; billing export. | PL-014 |  | P1 | Not Started | 0% | M
T-072 | R2 Enterprise evidence & governance | SaaS | Data residency (additional regions) | Tenant pinned to region; no cross-region writes. | PL-015 AC-041 |  | P1 | Not Started | 0% | L
T-073 | R2 Enterprise evidence & governance | SaaS | Per-tenant keys and BYOK | Envelope encryption per tenant; customer-managed KMS keys. | PL-016 |  | P1 | Not Started | 0% | M
T-074 | R2 Enterprise evidence & governance | SaaS | Dedicated SaaS deployment model | Single-tenant vendor-hosted stack from the same code. | PL-003 |  | P1 | Not Started | 0% | M
T-075 | R2 Enterprise evidence & governance | Platform | Graph-store benchmark and decision | PostgreSQL vs dedicated graph store at scale. | 12 |  | P1 | Not Started | 0% | M
T-076 | R2 Enterprise evidence & governance | Release | R2 security review, docs, quality gate | Per PRD 13/19. | PRD-19 |  | P1 | Not Started | 0% | M
T-077 | R3 Operational intelligence & scale | History | Temporal relationships and release comparisons | Introduced/removed/modified between releases. | FR-011 FR-030 AC-033 |  | P1 | Not Started | 0% | L
T-078 | R3 Operational intelligence & scale | Operations | Incident and rollback association | Association types; never auto root cause. | FR-031 AC-034 |  | P1 | Not Started | 0% | L
T-079 | R3 Operational intelligence & scale | Operations | Historical incident investigation | Changes/components relevant to an incident. | FR-032 AC-034 |  | P1 | Not Started | 0% | M
T-080 | R3 Operational intelligence & scale | Governance | Retention enforcement and audit reporting | Per data class. | 11.4 |  | P1 | Not Started | 0% | M
T-081 | R3 Operational intelligence & scale | Platform | High availability and horizontal scale | Independent API/worker scaling; no SPOF. | PL-004 |  | P1 | Not Started | 0% | L
T-082 | R3 Operational intelligence & scale | Platform | Backup, restore, disaster recovery | Documented RPO/RTO, tested. | PL-005 |  | P1 | Not Started | 0% | M
T-083 | R3 Operational intelligence & scale | Delivery | Customer-hosted and air-gapped installation | Same code in customer boundary; no outbound network required. | PL-010 |  | P1 | Not Started | 0% | M
T-084 | R3 Operational intelligence & scale | SaaS | SOC 2 Type II / ISO 27001 control set | Policies, evidence collection, pen test, incident runbooks. | PL-018 |  | P1 | Not Started | 0% | L
T-085 | R3 Operational intelligence & scale | Platform | Public versioned API, OpenAPI spec, client SDK | Stable external contract. | PL-008 |  | P1 | Not Started | 0% | M
T-086 | R3 Operational intelligence & scale | Release | R3 security review, docs, quality gate | Per PRD 13/19. | PRD-19 |  | P1 | Not Started | 0% | M
T-087 | R4 Extended coverage & advanced (GA) | Connectors | GitLab connector | MR analysis, comment, status, permissions. | FR-039 AC-036 |  | P2 | Not Started | 0% | L
T-088 | R4 Extended coverage & advanced (GA) | Connectors | Bitbucket connector | Data Center + Cloud. | FR-039 |  | P2 | Not Started | 0% | L
T-089 | R4 Extended coverage & advanced (GA) | Connectors | Azure DevOps Repos connector | PR analysis, comment, status. | FR-039 |  | P2 | Not Started | 0% | L
T-090 | R4 Extended coverage & advanced (GA) | Extraction | Adapter SDK | Documented interface for new languages. | FR-040 |  | P2 | Not Started | 0% | M
T-091 | R4 Extended coverage & advanced (GA) | Extraction | C#/.NET adapter | ASP.NET Core, HttpClient, EF. | FR-040 |  | P2 | Not Started | 0% | XL
T-092 | R4 Extended coverage & advanced (GA) | Extraction | TypeScript/JavaScript adapter | Express/NestJS, fetch/axios. | FR-040 |  | P2 | Not Started | 0% | XL
T-093 | R4 Extended coverage & advanced (GA) | Extraction | Go adapter | net/http, chi/gin. | FR-040 |  | P2 | Not Started | 0% | L
T-094 | R4 Extended coverage & advanced (GA) | Extraction | Kotlin adapter | Spring Kotlin. | FR-040 |  | P2 | Not Started | 0% | L | Java adapter
T-095 | R4 Extended coverage & advanced (GA) | Extraction | SQL and stored-procedure lineage | PostgreSQL, Oracle, SQL Server, DB2 dialects. | FR-041 AC-037 |  | P2 | Not Started | 0% | XL
T-096 | R4 Extended coverage & advanced (GA) | Extraction | Event-stream lineage | Multi-hop topics, stream jobs. | FR-042 |  | P2 | Not Started | 0% | L
T-097 | R4 Extended coverage & advanced (GA) | Analytics | Change-risk trends | Descriptive only, no probabilities. | FR-043 |  | P2 | Not Started | 0% | M
T-098 | R4 Extended coverage & advanced (GA) | Analytics | Calibration from validated outcomes | Reviewer verdicts, per-rule precision. | FR-044 AC-038 |  | P2 | Not Started | 0% | M
T-099 | R4 Extended coverage & advanced (GA) | Integration | Multi-team change coordination | Notify owners; track acknowledgement. | FR-045 |  | P2 | Not Started | 0% | M
T-100 | R4 Extended coverage & advanced (GA) | Release | R4 security review, docs, GA quality gate | Per PRD 13/19. | PRD-19 |  | P2 | Not Started | 0% | M

## Next Tasks
Next tasks to complete (ordered)
Driven by 'Next order' on Task Tracker (1 = do first). Renumber there and this list updates.
Order | ID | Task | Release | Requirement refs | Effort | Depends on | Status | Details / acceptance
1 | T-051 | PR comment + live verification via GitHub App | R1 Platform foundation & cross-repo impact | FR-035 AC-020 | S | GitHub App | Not Started | Update in place on push; never blocks merge.
2 | T-052 | Container images, Docker Compose, Helm chart | R1 Platform foundation & cross-repo impact | PL-009 | M | PostgreSQL, queue | Not Started | Images for SaaS and dedicated; documented data locations.
3 | T-053 | SaaS production environment (first region) | R1 Platform foundation & cross-repo impact | PL-009 PL-007 | L | Containers | Not Started | Infrastructure as code, gateway with tenant resolution and rate limits, managed PostgreSQL, evidence store, secrets, monitoring.
4 | T-054 | R1 release quality gate | R1 Platform foundation & cross-repo impact | PRD-19 | S | All R1 tasks | Not Started | All R1 ACs, accuracy, performance, security, operability, docs.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Requirements
Req ID | Requirement | Release | Status | Gap / notes | Tasks (IDs)
FR-001 | Repository connection | R1 | Partial | GitHub (App and PAT), Azure DevOps (PAT), git URL, local and upload ingestion done; GitHub App verified against a stand-in only; Azure DevOps webhooks/App-equivalent not built | T-017, T-018, T-028, T-041
FR-002 | Revision-aware analysis | R1 | Done |  | T-008
FR-003 | Incremental analysis | R1 | Done | Per-file incremental extraction + persisted versioned graph + full-rescan path with drift repair (Python) | T-025
FR-004 | Supported languages (Java + Python) | R1 | Partial | Java (Spring REST, JPA, Flyway/Liquibase) and Python (FastAPI/Flask, SQLAlchemy/Django ORM, Alembic/Django migrations) done; Django REST routes not extracted | T-009, T-029
FR-005 | Repository freshness | R1 | Done | Scan status, last successful scan, analysed revision, extractor version (snapshot), failures, stale relationships, inaccessible repos | T-026
FR-006 | Core graph entities | R1 | Partial | Service, endpoint, schema, function, call site, test, entity, table, column, migration done; deployment/build/event entities not built | T-030
FR-006a | Data-access scope (ORM/migrations) | R1 | Done | ORM mappings and migrations extracted; raw SQL/stored procedures (FR-041, R4) reported as data access not fully analysed | T-030, T-031
FR-007 | Execution and operations entities | R2 | Not started |  | T-059
FR-008 | Explicit relationship types | R1 | Done |  | T-007
FR-009 | Relationship provenance | R1 | Partial | No last-seen/validity yet (needs persisted graph)
FR-010 | Evidence classifications | R1 | Partial | stale now produced; runtime_observed (R6) never produced yet | T-007, T-026
FR-011 | Temporal relationships | R3 | Not started |  | T-077
FR-012 | Changed-symbol identification | R1 | Done | Python | T-009, T-029
FR-013 | Dependency traversal | R1 | Done |  | T-011, T-014, T-021
FR-014 | Cross-repository resolution | R1 | Partial | R1-R5 done; R6 runtime in R2 | T-010, T-060
FR-015 | Impact scope categories | R1 | Partial | Code, contract, test and data impact done; runtime/operational categories not built | T-014, T-032
FR-016 | Bounded traversal | R1 | Done |  | T-014
FR-017 | API discovery | R1 | Partial | FastAPI/Flask and Spring Web; endpoint authentication configuration not extracted | T-009, T-029
FR-018 | API contract comparison | R1/R2 | Partial | Basic P0 list done; full comparison R2 | T-012, T-058
FR-019 | Event and message contracts | R2 | Not started |  | T-059
FR-020 | Consumer impact report | R1/R2 | Partial | REST done; events R2 | T-059
FR-021 | Static test association | R1 | Done | Python | T-011
FR-022 | CI test results | R2 | Not started |  | T-055
FR-023 | Coverage enrichment | R2 | Not started |  | T-056
FR-024 | Regression recommendations | R2 | Not started |  | T-057
FR-025 | Missing-test evidence | R2 | Partial | Per-finding 'no relevant test evidence' limitation exists | T-057
FR-026 | Runtime integration | R2 | Not started |  | T-060
FR-027 | Runtime relationship classification | R2 | Not started |  | T-060
FR-028 | Deployment correlation | R2 | Not started |  | T-061
FR-029 | Environment-specific impact | R2 | Not started |  | T-061
FR-030 | Change history | R3 | Not started |  | T-077
FR-031 | Incident association | R3 | Not started |  | T-078
FR-032 | Historical investigation | R3 | Not started |  | T-079
FR-033 | Configurable policy rules | R2 | Not started |  | T-062, T-063
FR-034 | Policy evaluation | R2 | Not started |  | T-063
FR-035 | GitHub PR integration (comment + check) | R1/R2 | Partial | Comment upsert live-verified; publish endpoint and check run built, check run simulated only (needs GitHub App) | T-015, T-034, T-047, T-051, T-065
FR-036 | Advisory and enforcement modes | R2 | Not started |  | T-064
FR-037 | Assistant / MCP distribution | R2 | Not started |  | T-067
FR-038 | Change-management integration | R2 | Not started |  | T-066
FR-039 | Additional SCM platforms | R4 | Partial | ADO + generic git URL ingestion done by PAT; PR comment/status and permission mirroring for ADO/GitLab/Bitbucket pending | T-087, T-088, T-089
FR-040 | Adapter SDK + additional languages | R4 | Not started |  | T-090, T-091, T-092, T-093, T-094
FR-041 | SQL / stored-procedure lineage | R4 | Not started |  | T-095
FR-042 | Event-stream lineage | R4 | Not started |  | T-096
FR-043 | Change-risk trends | R4 | Not started |  | T-097
FR-044 | Calibration from validated outcomes | R4 | Not started |  | T-098
FR-045 | Multi-team change coordination | R4 | Not started |  | T-099
PL-001 | SSO OIDC/SAML, API tokens | R1 | Done | OIDC, SAML 2.0 and scoped service tokens built; verified against our own provider simulations only (no real IdP) | T-039
PL-002 | RBAC + SCM permission mirroring | R1 | Partial | Five roles + GitHub permission mirroring done (fake GitHub API); Azure DevOps mirroring not built | T-015, T-040
PL-003 | Multi-tenant isolation (shared schema + RLS) | R1 | Done | RLS on every tenant table, tenant resolved from the credential on every request, per-tenant workspace/quota/config/users; webhooks still use the default tenant | T-022, T-074
PL-004 | HA and horizontal scale | R3 | Not started |  | T-081
PL-005 | Backup / DR | R3 | Not started |  | T-082
PL-006 | Admin console + config API | R2 | Not started |  | T-069
PL-007 | Platform observability | R1 | Done | Metrics, JSON logs, traces, health/readiness built; verified against a fake OTLP collector only | T-037, T-053
PL-008 | Versioned public API + SDK | R3 | Partial | v1 REST endpoints exist; no OpenAPI publish/SDK | T-016, T-085
PL-009 | Containers, Helm, Compose | R1 | Not started |  | T-052, T-053
PL-010 | Air-gapped install | R3 | Not started |  | T-083
PL-011 | Encryption + secrets manager | R1 | Partial | Envelope encryption, scrubbing, TLS enforcement done; real Vault/KMS and PostgreSQL TLS not verified | T-036
PL-012 | Accessibility WCAG 2.1 AA | R2 | Not started |  | T-070
PL-013 | Tenant lifecycle | R1 | Done | Provision/suspend/resume/offboard with verified deletion + storage quota | T-033
PL-014 | Usage metering and plan limits | R2 | Not started |  | T-071
PL-015 | Data residency | R2 | Not started |  | T-072
PL-016 | Per-tenant keys / BYOK | R2 | Not started |  | T-073
PL-017 | Per-tenant fair scheduling | R1 | Done | Round-robin by queued position + exact per-tenant concurrency cap; verified on PostgreSQL | T-024
PL-018 | SOC 2 / ISO 27001 controls | R3 | Not started |  | T-084
PRD-9.2 | Impact path explorer / code graph | R2 | Partial | Explorer + impact overlay built (v0); filters by severity/evidence/environment, saved views, accessibility, large-scale clustering pending | T-020, T-021, T-068
11.3 | Audit | R1 | Partial | Tamper-evident keyed chain in PostgreSQL done; GitHub/ADO writes, logins and policy events audited when those features land | T-023, T-048
11.4 | Data retention | R3 | Not started |  | T-080
12 | Performance targets | R1-R3 | Not started | Unmeasured | T-075
15 | Accuracy targets | R1 | Partial | Measured on two independent real-code Java landscapes + a synthetic one: all measured targets met; time-saving not measured; no independent Python reference

## Acceptance Criteria
AC | Criterion (short) | Release | Status | Notes | Tasks (IDs)
AC-001 | Exact revisions | 1 | Done
AC-002 | Direct impact | 1 | Done
AC-003 | Transitive impact | 1 | Done
AC-004 | Contract impact | 1 | Done
AC-005 | Unresolved consumer | 1 | Done
AC-006 | Test association | 1 | Done
AC-007 | Runtime distinction | 2 | Not started |  | T-060
AC-008 | No false coverage claim | 2 | Not started |  | T-060
AC-009 | Failed scan | 1 | Done
AC-010 | Zero-impact result | 1 | Done
AC-011 | Stale relationships | 1 | Done |  | T-026
AC-012 | Bounded traversal | 1 | Done
AC-013 | Policy failure | 2 | Not started |  | T-063
AC-014 | Policy not evaluated | 2 | Not started |  | T-063
AC-015 | Reproducible evidence | 1 | Done | Snapshots materialised, pinned and reproduced identically (incl. after the landscape moved on) | T-027
AC-016 | Access control | 1 | Done | Per-reader redaction and 404 for unreadable repositories; GitHub mirror verified against a fake API, PR comment follows the readers rule | T-040
AC-017 | No invented entities | 1 | Done
AC-018 | Resolution transparency | 1 | Done
AC-019 | Inference labelling | 1 | Done
AC-020 | PR comment | 1 | Partial | Comment upsert live on github.com; check run simulated only | T-034, T-051
AC-021 | Incremental update | 1 | Done |  | T-025
AC-022 | Freshness | 1 | Done |  | T-026
AC-023 | Java analysis | 1 | Done |  | T-029, T-031
AC-024 | Data impact | 1 | Done |  | T-032
AC-025 | SSO and RBAC | 1 | Done | Roles enforced by a deny-by-default route table; tenant configuration (the policy stand-in) needs release_manager or administrator; every action audited with its actor; real IdP not used | T-039, T-040
AC-026 | GitHub App | 1 | Done | GitHub App JWT/installation tokens/routing/linking built and verified against a stand-in; no real GitHub App registered | T-041
AC-027 | CI evidence | 2 | Not started |  | T-055, T-056
AC-028 | Event impact | 2 | Not started |  | T-059
AC-029 | Deployed version | 2 | Not started |  | T-061
AC-030 | Enforcement mode | 2 | Not started |  | T-064
AC-031 | ITSM | 2 | Not started |  | T-066
AC-032 | MCP | 2 | Not started |  | T-067
AC-033 | Temporal query | 3 | Not started |  | T-077
AC-034 | Incident | 3 | Not started |  | T-078, T-079
AC-035 | Tenant isolation | 1 | Partial | Verified at storage layer (RLS tests) and at the API: the credential names the tenant, other tenants' reports, jobs and repositories answer 404 | T-022
AC-036 | Additional SCM | 4 | Not started |  | T-087
AC-037 | SQL lineage | 4 | Not started |  | T-095
AC-038 | Calibration | 4 | Not started |  | T-098
AC-039 | Tenant lifecycle | 1 | Done |  | T-033
AC-040 | Fair scheduling | 1 | Done |  | T-024
AC-041 | Data residency | 2 | Not started |  | T-072

## Use Cases
Use case | PRD ref | State | What works today | What is missing | Release | Tasks (IDs)
PR impact analysis | 5.1 FR-035 | Partial | Branch/PR analysis from GitHub, Azure DevOps, git URL, local path; findings, severity, unknowns, PR-comment markdown; impact graph | Automatic trigger on PR events (webhook), posting the comment back, check run, Java, ORM/data impact | R1/R2 | T-015, T-017, T-018, T-028, T-034, T-041, T-047, T-051, T-065
API contract change | 5.2 FR-018 FR-019 FR-020 | Partial | REST: removed/changed endpoint, removed/retyped response field, new required request field; consumers resolved via R1/R2/R3/R5 | Events and message schemas, full compatibility rules, OpenAPI ingestion, consumer-specific CI test evidence | R1/R2 | T-012, T-058, T-059
Explore the landscape (code graph) | 9.2 | Partial | Service / endpoint / function graph with evidence colouring, search, focus, impact overlay | Filters by severity/evidence/environment, saved views, large-landscape clustering, accessibility, persisted graph store | R1/R2 | T-020, T-021, T-068
Production incident investigation | 5.3 FR-031 FR-032 | Not started | - | Incident ingestion, deployment and runtime evidence, historical graph, association labels (never root cause) | R3 | T-077, T-078, T-079
Release-readiness assessment | 5.4 FR-033 FR-034 FR-036 | Not started | - | CI results, coverage, deployed versions, policy engine, advisory/enforcement mode, ITSM attachment | R2 | T-055, T-062, T-063, T-064, T-066
Assistant / MCP retrieval | FR-037 | Not started | REST API returns reports as JSON | MCP server, read-only tools | R2 | T-067
Governance and audit reporting | 11.3 11.4 | Not started | JSONL audit of analyses | Tamper-evident audit, retention enforcement, audit reports, RBAC | R1/R3 | T-015, T-023, T-040, T-048, T-080

## UC1 Definition of Done
Use case 1 - Pull-request impact analysis (PRD 5.1): definition of done
The use case is CLOSED only when every row is 'Verified (live)', or the user explicitly waives live verification for a row. Levels: Not started < In progress < Built < Verified (simulated: tests/fakes) < Verified (live: real GitHub / Azure DevOps / IdP). Rows marked LIVE-NEEDED cannot reach 'Verified (live)' without your credentials/accounts.
Progress | 16 live-verified, 11 simulated, 0 built, 0 in progress, 3 not started, of 30 |  |  |  |  | Use case closed? | OPEN
ID | PRD 5.1 step | Item (must all be true) | Requirement refs | Needs live external account | Status | Verified by | Notes
UC1-01 | all | Multi-tenant PostgreSQL storage: schema, migrations, forced RLS, non-owner app role, tenant context per transaction | PL-003 AC-035 TFD-9 |  | Verified (live) | tests/test_storage.py + app running on PostgreSQL | Real PostgreSQL 16.2 (embedded). Managed-PG/PgBouncer deployment not tested
UC1-02 | all | Tamper-evident (hash-chained, append-only) audit trail incl. external writes | 11.3 |  | Verified (live) | tests/test_storage.py + tests/test_auth_api.py (actor on every action, denials, logins); live: audit chain verified after sign-ins, token and role changes | Azure DevOps comment writes will be audited when UC1-15 is built
UC1-03 | 1 | Job queue on PostgreSQL: idempotent submission, retries, per-tenant fair scheduling, newest-revision-wins supersede | PL-017 AC-040 TFD-8/12 |  | Verified (live) | tests/test_jobs.py (20) + live dev server | Real PostgreSQL 16.2; webhook-triggered enqueue is UC1-05/06
UC1-04 | 1,2 | GitHub App connector: App JWT + installation tokens, repo registration, clone/fetch with installation token, permission-failure reporting | FR-001 AC-026 | LIVE-NEEDED | Verified (simulated) | tests/test_githubapp.py (51); live: CLI + API + worker processes against a GitHub platform stand-in | No real GitHub App registered; GitHub's real permission model and the user-authorisation redirect untested
UC1-05 | 1 | GitHub webhook receiver: HMAC signature verification, delivery-id idempotency, opened/synchronize/reopened/closed handling | FR-001 AC-026 | LIVE-NEEDED | Verified (simulated) | tests/test_webhooks.py: signature, parsing, guards, delivery dedupe, supersede, e2e; a locally signed delivery of the real sandbox PR updated its real GitHub comment | Delivery FROM github.com via a tunnel not done (cloudflared download blocked); closed/merged handling is a no-op; tenant from deployment until SSO
UC1-06 | 1,2 | Azure DevOps: service-hook receiver (PR created/updated) with auth verification, PR fetch, repo registration | FR-001 FR-039 | LIVE-NEEDED | Not started |  | Ingestion by PAT already works (simulated)
UC1-07 | 3,4 | Java / Spring adapter: routes, RestTemplate/WebClient/Feign, generated clients, tests | FR-004 FR-017 AC-023 |  | Verified (live) | tests/test_java.py (35) + real spring-petclinic-microservices code (54 files, 0 parse failures) | REST side only: AC-023 also needs JPA data access (UC1-08); see task notes for framework limits
UC1-08 | 4 | Python ORM and migration extraction (SQLAlchemy, Django ORM, Alembic, Django migrations) | FR-006 FR-006a |  | Verified (live) | tests/test_data.py + real django-realworld-example-app and fastapi full-stack template (schema replayed from migrations equals ORM columns exactly) | Raw SQL, Table() objects, dynamic table names, RunPython reported as unknown; see task notes
UC1-09 | 4 | Java ORM and migration extraction (JPA, Spring Data, Flyway/Liquibase) | FR-006a AC-023 |  | Verified (live) | tests/test_data.py + real spring-petclinic and jhipster-sample-app (Liquibase replay equals JPA columns exactly) | EntityManager/JDBC/jOOQ, procedural SQL, custom naming strategy, undeclared join tables reported as unknown; see task notes
UC1-10 | 4 | Data-impact traversal and findings (migration/schema change -> services via ORM mappings) | FR-015 AC-024 |  | Verified (live) | tests/test_data.py + live dev server on PostgreSQL (HTTP, queue+worker, 8 branches, reproduce identical) + real Chrome (impact overlay, search, 0 console errors) | Shared-database identity must be declared or come from a literal JDBC URL; column precision only for mapped columns; FR-041 (SQL lineage) not built
UC1-11 | 3,4 | Persisted versioned graph with incremental invalidation; full-rescan path; graph equals full rescan | FR-003 AC-021 |  | Verified (live) | tests/test_incremental.py + tests/test_graph_versions.py; also run live against the GitHub sandbox repos | Real PostgreSQL 16.2 + real git. Python adapter only; Java is UC1-07
UC1-12 | 6 | Stale-relationship handling and repository freshness tracking | FR-005 FR-010 AC-011 AC-022 |  | Verified (live) | tests/test_stale.py (6) incl. a real failed fetch and recovery | Real PostgreSQL + real git remotes (file URLs). A GitHub-side outage was not induced
UC1-13 | 6 | Evidence snapshots materialised; re-analysis on a snapshot is identical | AC-015 |  | Verified (live) | tests/test_snapshots.py (8); reproduced on the GitHub sandbox PR | Local repositories cannot be pinned
UC1-14 | 7 | GitHub: single PR comment updated in place + check run (advisory), via the App | FR-035 AC-020 | LIVE-NEEDED | Verified (simulated) | tests/test_publish.py, tests/test_webhooks.py (fake GitHub); comment upsert live on github.com earlier | Check run simulated only (needs GitHub App); posts with a PAT not the App; default audience hides downstream repo names
UC1-15 | 7 | Azure DevOps: PR thread comment (updated in place) + PR status | FR-035 FR-039 | LIVE-NEEDED | Not started
UC1-16 | 7 | Shareable report page per analysis in the UI (permalink linked from the PR comment) | PRD-9 |  | Verified (live) | tests/test_reportpage.py + real Chrome desktop and mobile
UC1-17 | 8 | Re-analysis on every push; a superseded analysis never overwrites the newer result on the PR | FR-002 AC-001 AC-020 |  | Verified (simulated) | tests/test_webhooks.py: new push updates the same comment; older queued run superseded, never comments | Depends on live webhook delivery for the real trigger; ADO equivalent is UC1-06/15
UC1-18 | all | SSO (OIDC and SAML 2.0) and service-account tokens | PL-001 AC-025 | LIVE-NEEDED | Verified (simulated) | tests/test_auth.py, tests/test_auth_api.py, tests/test_saml.py; live: real Chrome through a real OIDC flow on loopback | No real identity provider (OIDC or SAML) used; SHA-1 SAML refusal not exercised
UC1-19 | 7 | RBAC and SCM permission mirroring; findings from repos the reader cannot access never appear (incl. on the PR comment) | PL-002 AC-016 AC-025 | LIVE-NEEDED | Verified (simulated) | tests/test_access.py; live: four people, different repositories and redacted reports, mirror sync from a fake GitHub API | GitHub collaborators API is faked; Azure DevOps mirroring not built
UC1-20 | all | Tenant lifecycle: provision, SCM installation mapping, suspend, offboard with verified deletion | PL-013 AC-039 |  | Verified (live) | tests/test_tenants.py (21) + live admin CLI/API/worker on PostgreSQL | No real GitHub App installation event wired (UC1-04)
UC1-21 | all | Secrets management and encryption at rest/in transit; no secrets in graph or reports | PL-011 |  | Verified (simulated) | tests/test_credentials.py, tests/test_secretstore.py (fake Vault, test PKI) | Real Vault, KMS, PostgreSQL TLS not verified
UC1-22 | all | Platform observability: metrics, structured logs, traces, health/readiness | PL-007 |  | Verified (simulated) | tests/test_observability.py + live API/worker; fake OTLP collector | Real Prometheus/OTel collector not verified
UC1-23 | all | Container images, Docker Compose, Helm chart; SaaS environment definition | PL-009 |  | Not started |  | No Docker/Kubernetes in this environment: build files can be written, not run
UC1-24 | all | Configuration management: per-tenant limits, severity overrides, criticality, prefixes (versioned) | PRD-7.3 |  | Verified (live) | tests/test_tenantconfig.py (65) + live CLI->API->worker + real Chrome | No approval workflow/RBAC
UC1-25 | all | Reference landscape (Java + Python) with curated dependency set; accuracy harness; PRD 15.3 targets met | PRD-15 |  | Verified (live) | tools/accuracy.py on spring-petclinic-microservices and piggymetrics (real third-party code) + synthetic landscape; tests/test_accuracy.py | Java only for the independent references; small samples; assessment-time reduction not measured; configuration-dependent for context paths
UC1-26 | all | Performance benchmark meets PRD 12 targets | PRD-12 |  | Verified (live) | tools/benchmark.py at 500 repositories / 0.6 M lines on a real PostgreSQL; docs/PERFORMANCE.md | Generated landscape, 20 M LOC scan target not demonstrated; burst margin thin; availability/recovery not measured
UC1-27 | all | Security review and threat model; no open critical/high findings | PRD-19 |  | Verified (simulated) | docs/SECURITY.md + independent review + tests/test_security_review.py | Not an external pentest; M7 open (mitigated); several areas not independently reviewed
UC1-28 | all | Administrator, user, and API documentation | PRD-13 |  | Verified (simulated) | docs/ADMIN-GUIDE.md, USER-GUIDE.md, API.md + tests/test_docs.py | No field validation by real administrators or users
UC1-29 | all | CI pipeline for TIA itself | - |  | Verified (simulated) | tests/test_ci.py + the same gates run locally via tools/ci.py | Workflow never executed on GitHub Actions (no push); actions pinned by tag
UC1-30 | 1 | Code upload from the user drive: zip and whole folder, 2 GiB cap, each upload a revision analysed like a PR | FR-001 |  | Verified (live) | tests/test_upload.py (33) + real Chrome + live 721 MB streamed upload | Per-upload cap only; per-tenant storage quota later

## Decisions & Risks
Type | Item | Status | Detail | Owner / action
Decision | Scope | Confirmed by user (2026-10-29) | Enterprise product, not MVP/pilot; every PRD requirement mandatory for GA (PRD v3.0). | -
Decision | Release structure | Proposed by Claude | Four releases; GA = R4. Priorities P0/P1/P2 map to releases only. | You: confirm
Decision | Languages at R1 | Per PRD v3.0 | Java and Python both required in R1. | -
Decision | Delivery model | Confirmed by user (2026-10-29) | Multi-tenant SaaS (vendor-operated) + dedicated / customer-hosted option from the same code (PRD v3.1 11.2). | -
Decision | Tenant isolation | Confirmed by user (2026-10-29) | Shared schema, tenant_id on every row, PostgreSQL forced row-level security. | -
Decision | Dev/test database | Decided | Embedded PostgreSQL (pgserver 16.2) via tools/run_dev.py and the test suite; no SQLite anywhere. | Engineering
Decision | Primary datastore | Decided | PostgreSQL. Local dev/test uses the pgserver package (bundled binaries in Project TIA/.venv); Program Files/PostgreSQL holds only leftover data folders, no server. | Engineering
Decision | Performance/availability targets | Proposed | Values marked 'proposed' in PRD 12 need customer SLA confirmation. | You / customer
Risk | Size of scope | Open | Full GA scope is large (about 90 tasks, many L/XL). It will take many working sessions. | Plan staffing
Risk | External systems unavailable here | Open | No GitHub App credentials, IdP, ServiceNow, OTel backend, Docker, or Kubernetes in this environment: connectors can be built and tested with mocks/recorded fixtures but need live verification. | You: provide sandbox access
Risk | No real-world accuracy data | Open | Recall/precision unmeasured on real code. | Reference landscape task
Info | Effort figures | Info | S <1 day, M 1-3 days, L 3-10 days, XL >10 days; Claude's rough estimates. | Re-estimate with team
Info | Code layout rule | Info | Project TIA/tia = production code only; tests/, fixtures/, tools/ outside. | -

## Legend
Item | Meaning
Scope | Enterprise product per PRD v3.0. Every requirement is mandatory for GA; releases R1-R4 are delivery order, not optional tiers.
Blue cells | Inputs: Status, % Complete, Next order (Task Tracker); Status (Requirements, Acceptance Criteria); Last updated.
Task status | Completed / In Progress / Not Started / Blocked.
Requirement status | Done / Partial / Not started. 'Partial' always has a gap note.
Next order | 1 = do first. Next Tasks sheet reads it.
Effort | S <1 day, M 1-3 days, L 3-10 days, XL >10 days (rough).
Requirement refs | FR = functional, PL = platform, AC = acceptance criterion, numbers = PRD sections. Requirements and AC sheets list task IDs by these refs.
IDs | T-001... follow row order; inserting rows does not renumber.
Example row | T-020 ¦ R1 ... ¦ Platform ¦ PostgreSQL storage layer ... ¦ ... ¦ TFD-9 ¦ ¦ P0 ¦ Not Started ¦ 0% ¦ L ¦ ¦ 1 ¦ ¦ ¦